## Prioritization Tool
Team Members: |  | _________________________________ |  |  | Date: |  | _____________________________
Step 1: Characterization of Problem | [6 empty] | Step 2: Action Plan |  |  |  | Step 3: Results
Dept. | Problem | Potential Injuries or Ergonomic Risks | SEV1 | Potential Productivity Risks | SEV2 | Priority | Reccomended Actions | Tool to Be Used | Start Date | End Date | Actions Taken | SEV1 | SEV2 | Priority
A | Unpacking sub assembly X | Back strain (several injuries) | 3 | Slow unloading time | 2 | #NAME? | Review process, ergo analysis | Mod VSSM | 2016-09-10 | 2017-10-10 | Conducted REBA analysis, lift belts and two-man lift | 2 | 2 | #NAME?
B | Spot welds on top of unit | Bending, crouching for extended period | 2 | Infrequent Rework | 2 | #NAME? | Station redesign | Mod VSSM | 2016-09-10 | 2017-10-10 | Unit rotated, upright posture adopted | 1 | 1 | #NAME?
A | Carrying RM bags | Poor coupling, hand strain | 2 | Delays to re-grip | 1 | #NAME? | Research carrying tools | Mod VSSM | 2016-09-10 | 2017-10-10 | Purchase power grip carrying hooks | 1 | 1 | #NAME?
C | Manual Picking | Height of shelves, overhead lift | 3 | Drops or delays for assist ftom team member | 1 | #NAME? | Consider item placement, station redesign study | Mod VSSM | 2016-09-10 | 2017-10-10 | Lighter objects highest, shelf height dropped | 2 | 1 | #NAME?
[6 empty] | #NAME? | [7 empty] | #NAME?
[6 empty] | #NAME? | [7 empty] | #NAME?
[6 empty] | #NAME? | [7 empty] | #NAME?